## Summary
INDEPENDENT REVIEW
Project Title: | Poynton Relief Road |  | Scheme Promoter: | Cheshire East Council
Document Reviewed: | Outline Business Case |  | Permission Sought:
Date of Submission: |  |  | Date of Review: | 2019-01-31
LEP Accountability Framework:
Scheme Description: | New road from A523 at Addlignton to A6 MARR at Woodford bypassing Poyton
SUMMARY SHEET
Overall Score: | 2 |  |  | 1 | Requirements fully met - No issues of note with the submission, project to progress as scheduled.
Overall Comments: | This review has been undertaken as though for an Outline Business Case. Three of the five cases require minor improvements. There are more substancial questions associated with the economic case, and modelling improvements are likely to be required as the schemes moves into FBC stage |  |  | 2 | Requirements substantially met - Minor issues exist with the submission. Project to progress and issues to be resolved.
|  |  |  | 3 | Requirements partially met - Medium issues exist with the submission. Project to progress and issues to be resolved urgently.
|  |  |  | 4 | Requirements not met - Critical issues exist with the submission. Project to be suspended whilst issues are resolved.
Case | Status | SYSTRA Comments
Strategic Case | 2 | Strategic case generally formed, however the framework for measuring against objectives is not well-defined. No evidence of consultation with major stakeholders
Economic Case | 2 | Some risks with the transport modelling and economic assumptions. Base scheme costs are from 2015 Q4. Whilst escalation has been considered, it is advisable to review. Social and Distributional Impacts not yet analysed | 0 | 1 | Requirements fully met - No issues of note with the submission.
Financial Case | 2 | Financial case broadly acceptable. However no funding sources are identified within the submission. These are required to be included at this stage. Base scheme costs are from 2015 Q4. Whilst escalation has been considered, it is advisable to review. S151 officer sign-off is not evidenced | 0 | 1 | Requirements fully met - No issues of note with the submission.
Commercial Case | 1 | Noted that procurement workshop was undertaken three years ago, however otherwise commericial case meets requirements. It is not clear whether the programme and milestone dates are up to date. | 0 | 1 | Requirements fully met - No issues of note with the submission.
Management Case | 2 | Management case broadly meets requirements, however elements on statutory powers, risks and stakeholder engagement all require additional detail | 0 | 1 | Requirements fully met - No issues of note with the submission.
Sign-Off
Reviewer's Signature: | 1 |  | Date: | 2019-01-31

## Strategic Case
INDEPENDENT REVIEW
Project Title: |  |  |  | Poynton Relief Road
Permission Sought: |  |  |  | 0 |  | Date of Review: | 2019-01-31
STRATEGIC CASE
Overall Score |  |  |  | 2 |  |  | 1 | Requirements fully met - No issues of note with the submission.
Comments: |  |  |  | Strategic case generally formed, however the framework for measuring against objectives is not well-defined. No evidence of consultation with major stakeholders |  |  | 2 | Requirements substantially met - Minor issues exist with the submission.
[7 empty] | 3 | Requirements partially met - Medium issues exist with the submission.
[7 empty] | 4 | Requirements not met - Critical issues exist with the submission.
Ref | Item | Applicable Guidance | Key relevant sections in Business Case | FBC Status | Comments
S1 | Is there a clear description of the components of the scheme and how it fits with the aims and objectives of the LEP, Local Authorities and DfT? | DfT Transport Business Case Guidance - Chapter 2 | 2.7 | Requirements Substantially Met | Fit with aims and objectives clear for Cheshire East Council. Objectives are listed for other organisations, however the scheme is not "tested" against these objectives to explain how PRR will support achieving these
S2 | Have the problem(s) the scheme will be addressing been clearly identified – including evidence of the extent of the problem(s), specific barriers / challenges, and how the scheme will overcome them (including the scale of impact) | DfT Transport Business Case Guidance - Chapter 2 | 2.2-2.4 | Requirements Substantially Met | Some evidence, however evidence of expected traffic volumes is at the whole model level, which includes many trips which do not travel through Poynton (2.3.3). Observations on the identified problems around Poynton are not fully quantified.
S3 | Has the impact of not progressing the scheme been set out, including supporting evidence? Is there adequate rationale to support why the scheme is needed now? | DfT Transport Business Case Guidance - Chapter 2 | 2.4.3 | Requirements Fully Met
S4 | Is there a set of specific, measurable, achievable, realistic, time-bound (SMART) objectives for the scheme to address the problem(s) identified? | DfT Transport Business Case Guidance - Chapter 2 | 2.5.5 | Requirements Substantially Met | Scheme specific objectives are defined. A framework is defined for measuring performance against the objectives with further detail in Chapter 7 (Monitoring and Evaluation and Benefit Realisation). Specific targets are not defined
S5 | Are the expected outcomes clear - How will it be possible to know when the objectives have been met, and what will ‘success’ actually mean? | DfT Transport Business Case Guidance - Chapter 2 | 2.5.5 | Requirements Substantially Met | A framework is defined for measuring performance against the objectives, however specific targets are not defined.
S6 | Is it clear what the project is expected to deliver on the ground, including what is in scope and what is out of scope? | DfT Transport Business Case Guidance - Chapter 2 | 2.6.4 and 2.6.5 | Requirements Fully Met | Limit of main scheme clear and "A523 Online Highway Improvements" are clearly described. A figure showing the location of Adlington Crossroads and Bonis Hall Lane Junction would be helpful for readers unfamiliar with the area.
S7 | Have any high-level constraints affecting the ability of the scheme to solve the problem(s) been identified? | DfT Transport Business Case Guidance - Chapter 2 |  | Requirements Not Met | No comment on high-level constraints
S8 | Have any interdependencies which may affect the success of the scheme been identified? | DfT Transport Business Case Guidance - Chapter 2 |  | Requirements Fully Met | Interdependencies with other transport schemes and development proposals identified
S9 | Have relevant studies and technical work that has informed the development of the scheme been identified? |  | 2.6 | Requirements Fully Met | Previous studies and scheme history identified
S10 | Are any links with other schemes clear and has the 'in-combination' impact been considered? | DfT Transport Business Case Guidance - Chapter 2 | 2.12 | Requirements Fully Met | Synergy with A6MARR and Congleton Link Road considered
S11 | Have the main stakeholder groups and their contribution to the project been defined? This should include any potential conflicts between different stakeholder groups and their demands. | DfT Transport Business Case Guidance - Chapter 2 | 2.10 | Requirements Partially Met | Mention made of stakeholder meetings, but limited detail and no assessment of views raised. There is no evidence that stakeholders such as Natural England, English Heritage, Highways England (PRR is modelled to increase traffic on parts of the M60) or neighbouring councils (aside from Stockport MBC) have been consulted.
S12 | Is there a robust assessment of different scheme options, including the reasons for any options being discounted? Has an EAST options appraisal been undertaken? | The Transport Appraisal Process | 2.6.5 | Requirements Substantially Met | Proportionate approach undertaken as scheme concept is mature and has undertaken previous option assessments, in particular the SEMMMS multi-modal study. EAST not undertaken
S13 | Have details of stakeholder and public consultation been provided? | DfT Transport Business Case Guidance - Chapter 2 | 2.1 | Requirements Partially Met | Stakeholder consultations mentioned, for a route option and pre-planning application consultantion, but no details on dates or attendees. Public consultation details included, but undertaken in 2014/15 As per item S11 it is not clear whether some important stakeholders have been consulted.

## Economic Case
INDEPENDENT REVIEW
Project Title: |  |  |  | Poynton Relief Road
Permission Sought: |  |  |  | 0 |  | Date of Review: | 2019-01-31
ECONOMIC CASE
Overall Score |  |  |  | 2 |  |  | 1 | Requirements fully met - No issues of note with the submission.
Comments: |  |  |  | Some risks with the transport modelling and economic assumptions. Base scheme costs are from 2015 Q4. Whilst escalation has been considered, it is advisable to review. Social and Distributional Impacts not yet analysed |  |  | 2 | Requirements substantially met - Minor issues exist with the submission.
[7 empty] | 3 | Requirements partially met - Medium issues exist with the submission.
[7 empty] | 4 | Requirements not met - Critical issues exist with the submission.
Ref | Item | Applicable Guidance | Key relevant sections in Business Case | FBC Status | Comments
E1 | Has a Value for Money Statement been provided, including a BCR? | TAG Unit A1.1 – Cost Benefit Analysis | 3.7 | Requirements Fully Met | Yes, based on evidence in Economic Assessment Report
E2 | Are there any key assumptions relating to how the BCR has been derived? | TAG Unit A1.1 – Cost Benefit Analysis | 3.3 and Economic Assessment Report | Requirements Fully Met | The Economic Assessment Report (September 2018) provides detail Key assumptions are included. Of these, some are queried: 2.3 - the opening year is stated as 2020 3.2 and 5.2.1 have inconsistent definitions of the IP period 5.2.1 - the annualisation factors for TUBA in table 5-1 are inconsistent with the period designations given following figure 5-1. 5.2.2 - national OGV1 and OGV2 splits used, however LMVR implies the PCU factor for OGV is based on a locally observed fleet mix
Benefits
E3 | Is the basis for the calculation of the Present Value of Benefits (PVB) sufficiently robust? Has sufficient information been provided on how this has been derived? | TAG Unit A1.1 – Cost Benefit Analysis | 3.5 and EAR | Requirements Fully Met | Economic Assessment Report Information given on how this is derived fairly robust. There are however some areas which require investigation Table 5-6 - description of warnings in DM includes an explanation about DS. Also explanation that speeds over limit not appropriate if buffer is correctly coded for both time and distance Table 5-8 - the explanation for DM to DS travel distance higher than limit is "re-routing of some trips opting to take a more direct and shorter route", which leads to a decrease in the ratio 5.5 "Where a junction had no accidents of the five-year period the default accident rate was applied to the junction..."
Costs
E4 | Is the basis for the calculation of the Present Value of Cost (PVC) sufficiently robust? Has sufficient information been provided on how this has been derived? | TAG Unit A1.2 – Scheme Costs | 3.4 | Requirements Substantially Met | Basis generally sound, however some queries on profile. Costs after business case approval commence in 2014, with 12% spent by end-2019, and construction is spread across 2020 and 2021, with the scheme assumed fully open in 2020. Costs were estimated in 2015 Q4 prices. An allowance has been made for real terms cost escalation. The weaker pound, post-Brexit referendum, may impact on costs. It would be advisable to review the costs for the FBC stage. Reduction in the maintenance of existing roads is subtracted from the total maintenance cost with no evidence for what proportion of expected expenditure this represents.
E5 | Has an appropriate level of optimism bias been applied? |  | 3.4 | Requirements Fully Met | Optimism bias of 15% applied, in line with WebTAG for OBC stage. At FBC, the appropriate value is 3%
E6 | Has an appropriate level of risk cost been included? |  | 3.4 and 4.5 | Requirements Fully Met | A brief description of the QRA is given in the Financial Case. The approach appears consistent with good practice.
Modelling, Forecasting & Economic Analysis
E7 | Is the traffic modelling and forecasting approach / tools sufficiently robust? | TAG Unit A5.5 – Highway Appraisal | Forecasting Report (TfGM, June 2017) | Requirements Partially Met | See sheet "E7 Comments"
E8 | Have all other modelling assumptions been made clear? | TAG Unit M1.1 – Principles of Modelling and Forecasting | Forecasting Report (TfGM, June 2017) | Requirements Substantially Met | Forecasting Report Geographic model extent is not shown. Query as to whether forecasting assumptions are appropriately updated from the A6 to M60 scheme as "Poynton Relief Road" is shown as a Likely scheme and "included in Do Minimum Highway Scheme assuptions".
E9 | Has relevant supporting documentation been provided to substantiate that modelling undertaken is fit for purpose? (e.g. data / traffic surveys report, LMVR, Forecasting Report) | TAG Unit M3.1 – Highway Assignment Modelling | Forecasting Report (TfGM, June 2017) | Requirements Fully Met | Documents received, subject to comments above/below DfT has reviewed some of the documents as noted under point E7
E10 | Are TUBA outputs robust? | TAG Unit M4 – Forecasting and Uncertainty | Economic Assessment Report and Analysis of Sectored TUBA Benefits | Requirements Substantially Met | Economic Assessment Report Little evidence provided on the robustness of TUBA outputs. Warnings are addressed by class but are not described geographically. Spatial distribution of TUBA benefits have been analysed and reported. The sector system could be better tailored to PRR. The sector-pairs with the largest benefits appear plausible. Some issues could be investigated further including why the all day benefits are asymetrical (benefits from sector X>Y are very different to Y>X in general).
E11 | Have all relevant options been modelled / appraised? | TAG Unit M2 – Variable Demand Modelling | Forecasting Report | Requirements Substantially Met | Modelling results only shown for prefered scheme. However results for the alternative alignments would be expected to be broadly similar.
E12 | Have appropriate sensitivity tests been undertaken? | TAG Unit A1.3 – User and Provider Impacts | Economic Assessment Report | Requirements Substantially Met | Economic Assessment Report Appriopriate sensitivity tests on growth assumptions defined and undertaken. However no exploration into how the high growth sensitivity generates benefits three times higher than the central case and if this is appropriate. Only TUBA analysis done for low and high growth scenarios. All other impacts that relate to traffic levels (including noise, AQ, GHG, accidents, tax revenues) would differ between core, low and high growth scenarios. However the monetised values of these impacts is much lower than the impacts calculated using TUBA.
Scheme Impacts
E13 | Has a completed AST been provided (with supporting worksheets where relevant)? | Guidance for the Technical Project Manager | AST Report | Requirements Substantially Met | 3.7.1 states "The AST for PRR scheme, which summarises the information contained within the Economic Case, is included in the Economic Assessment Report". Cannot find standard AST in the EAR. Separate AST report provided. Supporting worksheets are not included in the EAR or AST reports
E14 | Has sufficient justification been provided on scoping out of any specific impacts? | Guidance for the Technical Project Manager | n/a | Requirements Partially Met | Exclusion of qualitative measures not justified. Includes: - landscape - townscape - historic environment - Biodiversity - Social benefits except Commuting and Other Users
E15 | Has sufficient justification been provided on the approach used to appraise each impact (e.g. quantitative / qualitative)? | Guidance for the Technical Project Manager | EAR | Requirements Fully Met | Generally yes, however no explanation as to the approach to Wider Impacts. The DfT also raised a query as to whether the version of COBALT inputs used is appropriate
E16 | Have all (relevant) Economic Impacts been adequately assessed and are the ratings (seven-point scale) reasonable? | TAG Unit A1.3 – User and Provider Impacts |  | Requirements Substantially Met | All Impacts assessed, however the seven-point scale for SDI impacts are "TBC"
TAG Unit A2.1 – Wider Impacts
TAG Unit A2.2 – Regeneration Impacts
E17 | Are forecast housing, jobs and GVA impacts provided robust / realistic? |  | Forecasting Report Section 4 & OBC 3.6 | Requirements Partially Met | Forecast housing and jobs inputs appear appropriate in aggregate, however the impact at the individual purposes at the time period level in the cordon model are not all intuative. For example, Car EB growth from base is 6% (AM), 2% (IP) and 10% (PM) but by 2035 this is 12% (AM), 11% (IP) and 11% (PM). There is no explanation for the inconsistent gorwth in the IP and PM peaks. Details of the development assumptions are not reported. Section 3.6 of the OBC presents GVA benefits of £116m over the 60 year appraisal. The methodology and assumptions are not presented in the OBC or EAR. GVA benefits are not included in the calculation of PVB so do not impact on the calculated BCR and NPV.
E18 | Have all (relevant) Environmental Impacts been adequately assessed and are the ratings (seven-point scale) reasonable? | TAG Unit A3 – Environmental Impact Appraisal | AST Report | Requirements Partially Met | All Impacts assessed, however the seven-point scale assessments for SDIs are "TBC"
E19 | Have key environmental constraints been clearly identified? | TAG Unit A3 – Environmental Impact Appraisal | 2.2 & 3.5.5-3.5.7 | Requirements Fully Met | Environmental impact assessed, and disbenefit recorded. Environmental constraints considered (section 2.2)
E20 | Have all (relevant) Social Impacts been adequately assessed? and are the ratings (seven-point scale) reasonable? | TAG Unit A4.1 – Social Impact Appraisal | AST Report | Requirements Partially Met | All Impacts assessed. Journey Quality - benefit of a decreased fear of accidents despite a forecast increase in fatal accidents Physical Activity - beneficial impact from the slightly increased journey times for users of some of the PRoW Social Distributional Impact Analysis has not been done
E21 | Have Distributional Impacts been assessed in a robust manner? | TAG Unit A4.2 – Distributional Impact Appraisal |  | Requirements Not Met | Not assessed, and lack of inclustion not justified

## E7 Comments
Review of Traffic Data Collection Report and Local Model Validation Report
DfT’s Economics of Regional and Local Transport team has reviewed the TDCR and LMVR, and CEC has responded to DfT’s comments. Most of the comments have been resolved to DfT’s satisfaction. The outstanding comments relate to how base year matrices were developed, including the use of mobile phone data. Additional documentation will be provided to DfT for review. Therefore at present DfT has not provided a definitive view on the acceptability of the matrices. SYSTRA's remit for the Independent Review excluded reviewing the DCR and LMVR (as reviews have been done by DfT).
Forecasting Report
Appropriate software tools have been applied, and the forecasting framework and highway modelling are broadly appropriate. However there are some areas for improvement:
Paras 3.21-3.22 discuss surface access scheme and public transport mode share targets for Manchester Airport. It is not clear if, or how, these have been reflected in the modelling.``
Chapter 4 provides an overview of the forecasting assumptions and refers (para 4.4) to a WSPPB report undertaken for the A6 to M60 Relief Road Study. It would be helpful if a summary of the developments included in forecasting, their scale and nature, the level of trip generation, mode share assumptions, etc were documented.
Para 4.16 states that the VDM assessment was carried out at an origin-destination level. However WebTAG Unit M2, 2.5.2 states that VDM should be undertaken at production-attraction level unless the DfT have given prior approval to use origin-destination. Is there documentation of this approval for Poynton Relief Road? Related to this from para 5.7 and in appendix A there are tidality inconsistencies with the forecast cordon crossings. To illustrate, on SEMMS Cordon 3, which contains Poynton, there is a 1-2% increase in demand inbound, but a 10-14% increase in demand outbound. A summary table of the cordon crossings would make this much easier to analyse. We note that TfGM holds PA matrices for the GMVDM area and these could be sectored and applied to the PRR cordon model
Para 4.17 says that the variable demand model was applied for a cordoned version of the model. A map of the cordoned area is not provided. Ideally the VDM would cover a wider area becasue of the interactions (including commuting) between the Poynton area and the Greater Manchester conurbation. We appreciate that the decision to apply VDM for the cordon level was pragmatic and proportionate, but could raise questions from DfT.
Mode choice is not applied in the VDM (para 4.21). Again this may be reasonable and proportionate in the context, but there is significant rail demand from Poynton (inclduing using Bramhal, Hazel Grove and Macclesfield stations). DfT may seek more detailed justification of this decision.
Model calibration (para 4.25-5.26):
- the sensitivity of the frequency response is not documented
- the model has been calibrated to a fuel cost elasticity of -0.3 (as advised in TAG). This elasticity is appopriate in a context where mode choice is modelled, so may somewhat overstate the distribution effect in the PRR cordon model (where mode choice is excluded).
- fuel cost elasticities should be reported separately by trip purpose: non-discretionary purposes are expected to be less elastic
- a travel time elasticity sholuld be reported to satisfy WebTAG advice (although it is rare for models not to meet the DfT elastcity requirement)
Para 4.42 presents a gap statistic which is very close to the level of change associated with the scheme, when WebTAG recommends it should be around 10% of the change. In our experience it is unlikely that a SATURN/DIADEM model of the size and nature developed for PRR could meet the WebTAG 10% target, so this does not necessarily mean that DfT would have serious concerns. To provide confidence that the aggregate level of change is robust, further evidence such as sectored demand changes showing that changes occur on movements expected to benefit from the scheme would be beneficial. Sectored TUBA outputs have been anaysed to provide a degree of confidence. Additionally, the delta value seems high, unless this should be labelled as a percentage.
The final column in Tables 4.5 - 4.7 appears to be mislabled. The numbers appear to show the percentage change between the without-PRR to with-PRR (not fixed to with-PRR as stated)
Para 5.20 onwards discusses the journey time routes, 31 routes are shown on the map, but results are only shown for 14. Some of those excluded are closer to the scheme than others which are included, but no rationale is given for the selection. The description of the journey time impacts are fully described for decrease, but then does not describe all of those links which have a significant increase in journey times, which in the PM peak is a larger proportion than those with a significant decrease, which could give a misleading impression on the performance of the highway network following the introduction of the scheme.
Section 7: includes references to NTEM 6.2 and 7. Chapeter 4 refers to version 7.2 which is the latest verion. This could be a simple typo in section 7 - it appears the current version has been used.
The modelled "area of influence" is not shown within the report. If it is the area shown in Figure 1-2 of the EAR, query as to whether this is appropriate for the scheme. It includes a large proportion of the southern M60, but does not extend fully through Macclesfield. This has the afftect that large flow changes nearly reach the southern boundary, whilst a large amount of model noise on the M60, well beyond the large flow changes is included.

## Financial Case
INDEPENDENT REVIEW
Project Title: |  |  |  | Poynton Relief Road
Permission Sought: |  |  |  | 0 |  | Date of Review: | 2019-01-31
FINANCIAL CASE
Overall Score |  |  |  | 2 |  |  | 1 | Requirements fully met - No issues of note with the submission.
Comments: |  |  |  | Financial case broadly acceptable. However no funding sources are identified within the submission. These are required to be included at this stage. Base scheme costs are from 2015 Q4. Whilst escalation has been considered, it is advisable to review. S151 officer sign-off is not evidenced |  |  | 2 | Requirements substantially met - Minor issues exist with the submission.
[7 empty] | 3 | Requirements partially met - Medium issues exist with the submission.
[7 empty] | 4 | Requirements not met - Critical issues exist with the submission.
Ref | Item | Applicable Guidance | Key relevant sections in Business Case | FBC Status | Comments
F1 | Is the expected whole life cost of the scheme robust, including the base cost and risk allowance in out-turn prices drawn from industry forecasts? | TAG Unit A1.2 – Scheme Costs | 4.4 | Requirements Partially Met | Costs based on Q4 2015 prices. Construction costs increased substancially during 2016
F2 | Has a cost profile been provided showing year on year costs, and breakdown by cost type and parties on whom they fall? | DfT Transport Business Case Guidance - Chapter 4 | EAR | Requirements Substantially Met | Cost profile not included in financial case. Cost profile in economic assessment report does not appear up to date
F3 | Have details of key financial risks been provided and is the risk cost allowance robust? | TAG Unit A1.2 – Scheme Costs | 4.5 | Requirements Fully Met | QRA briefly summarised. Approach seems in line with good practice
F4 | Are funding sources to cover the full scheme cost clearly set out? | DfT Transport Business Case Guidance - Chapter 4 |  | Requirements Not Met | Funding sources not described
F5 | Is there sufficient evidence to support third party / alternative funding contributions? | DfT Transport Business Case Guidance - Chapter 4 |  | Requirements Not Met | No third party funding contributions identified. It is noted that the AMCB tables in the EAR show developer contributions (£5m), but these are not mentioned in the financial case. Local authority, LEP and DfT budgets are likely to cover the remainder of the costs
F6 | Have the impacts of third party / alternative funding not coming forward been considered? | DfT Transport Business Case Guidance - Chapter 4 |  | Requirements Not Met | See item F5. Source of third party funding contributions not specified.
F7 | Has the the long-term financial sustainability of the scheme been demonstrated, including robust plans to ensure the affordability of any ongoing costs for operation, maintenance and major capital renewals? | TAG Unit A1.2 – Scheme Costs | EAR 4.4 | Requirements Fully Met | Maintenance costs have been assessed using QUADRO. Maintenance costs for PRR are partially offset by reduced maintenance requirements for existing roads. The net impact is £1.9m (2015, not discounted) over 60 years, ie a very modest £32k pa. Noted that table 4-4 is not very clear, ideally the second row would be shown as negative
F8 | Has evidence of appropriate S151 Officer sign-off been provided? |  |  | Requirements Not Met | Sign-off not present

## Commercial Case
INDEPENDENT REVIEW
Project Title: |  |  |  | Poynton Relief Road
Permission Sought: |  |  |  | 0 |  | Date of Review: | 2019-01-31
COMMERCIAL CASE
Overall Score |  |  |  | 1 |  |  | 1 | Requirements fully met - No issues of note with the submission.
Comments: |  |  |  | Noted that procurement workshop was undertaken three years ago, however otherwise commericial case meets requirements. It is not clear whether the programme and milestone dates are up to date. |  |  | 2 | Requirements substantially met - Minor issues exist with the submission.
[7 empty] | 3 | Requirements partially met - Medium issues exist with the submission.
[7 empty] | 4 | Requirements not met - Critical issues exist with the submission.
Ref | Item | Applicable Guidance | Key relevant sections in Business Case | FBC Status | Comments
C1 | Has a robust procurement strategy been clearly set out? | DfT Transport Business Case Guidance - Chapter 5 | 5.4 | Requirements Fully Met
C2 | Has consideration of different procurement options been demonstrated, including justification for selection of the preferred option? | DfT Transport Business Case Guidance - Chapter 5 | 5.2 | Requirements Substantially Met | Consideration via a procurement workshop in May 2015. Query as to whether the conculsions from this remain current given events in 2016-2018. For example different public sector frameworks may be available
C3 | Have the proposed payment mechanisms / pricing framework been identified? | DfT Transport Business Case Guidance - Chapter 5 | 5.6 | Requirements Fully Met
C4 | Have the procurement timescales been set out, and are they realistic? | DfT Transport Business Case Guidance - Chapter 5 | 5.10 | Requirements Substantially Met | Timescales given. OJEU launched is stated as 23rd October 2018 and award in October 2019. Clarification of whether this programme is up-to-date would be helpful.
C5 | Have details of the proposed risk transfer / allocation been provided? | DfT Transport Business Case Guidance - Chapter 5 | 5.9 | Requirements Fully Met | Design and build procurement approach planned.
C6 | Have details of contract management been provided, including contract timescales? | DfT Transport Business Case Guidance - Chapter 5 | 5.8/6.5 | Requirements Fully Met | Key milestones identified in delivery plan. Clarification of whether the programme is up-to-date would be helpful
C7 | Has evidence of relevant approval been provided from Head of Procurement? | DfT Transport Business Case Guidance - Chapter 5 | 5.5 | Requirements Fully Met | Approval from Cheshire East Council Cabinet

## Management Case
INDEPENDENT REVIEW
Project Title: |  |  |  | Poynton Relief Road
Permission Sought: |  |  |  | 0 |  | Date of Review: | 2019-01-31
MANAGEMENT CASE
Overall Score |  |  |  | 2 |  |  | 1 | Requirements fully met - No issues of note with the submission.
Comments: |  |  |  | Management case broadly meets requirements, however elements on statutory powers, risks and stakeholder engagement all require additional detail |  |  | 2 | Requirements substantially met - Minor issues exist with the submission.
[7 empty] | 3 | Requirements partially met - Medium issues exist with the submission.
[7 empty] | 4 | Requirements not met - Critical issues exist with the submission.
Ref | Item | Applicable Guidance | Key relevant sections in Business Case | FBC Status | Comments
M1 | Has the proposed governance / organisational structure been provided? Does it provide a robust means of overseeing project delivery with appropriate skills / experience? | DfT Transport Business Case Guidance - Chapter 6 | 6.2 | Requirements Fully Met
M2 | Does the project programme demonstrate realistic delivery timescales? Does it provide an appropriate level of detail, eg in GANTT chart form? | DfT Transport Business Case Guidance - Chapter 6 | 6.5 | Requirements Substantially Met | These is a programme. No GANTT chart, unclear if realistic or up-to-date
M3 | Have critical path items and dependencies been clearly identified? | DfT Transport Business Case Guidance - Chapter 6 | 6.3 | Requirements Fully Met
M4 | Have required statutory powers and consents been identified, including current status and timescales for obtaining these powers if they are not already in place? | DfT Transport Business Case Guidance - Chapter 6 | 6.5 | Requirements Substantially Met | Statutory powers listed as key milestones, but not otherwise identified
M5 | Have details of the reporting, assurance and approval process been provided (including gateways in scheme development / delivery)? | DfT Transport Business Case Guidance - Chapter 6 | 6.3 | Requirements Substantially Met | Gateways identified, but only 1 and 2 have been defined. No other detail on reporting process
M6 | Has evidence of scheme delivery been provided, to demonstrate that the delivery body has the capability and means to successfully implement the scheme? | DfT Transport Business Case Guidance - Chapter 6 | 6.7 | Requirements Fully Met | Evidence of similar projects provided
M7 | Has a Risk Management Strategy been provided, setting out how risks have been identified, their likely impact, appropriate mitigation, and how the risks will be managed (and by whom)? | DfT Transport Business Case Guidance - Chapter 6 | 6.6 | Requirements Fully Met | QRA undertaken and to be updated when risks change. Governance processes deal with management of risk.
M8 | Have key risks been identified and are suitable mitigation measures proposed? | DfT Transport Business Case Guidance - Chapter 6 | 4.5 & 6.6 | Requirements Fully Met | Top 5 risks, and mitigations, are listed in the Financial Case. Contingency plan included.
M9 | Is there a Stakeholder Management Plan that identifies key stakeholders and details how engagement / consultation will be undertaken? | DfT Transport Business Case Guidance - Chapter 6 | 6.8 | Requirements Partially Met | States that a stakeholder engagement plan exists, but no details given
M10 | Does the scheme have support? Is it likely to be acceptable? | DfT Transport Business Case Guidance - Chapter 6 | 6.9 | Requirements Fully Met | Scheme had high levels of support (95%) at public consultation. Public consultations were held for Route Option and Pre-Planning phases (section 2.10).
M11 | Is there a clear intervention logic for how the outcomes will be achieved? (e.g. logic map) | DfT Transport Business Case Guidance - Chapter 6 | 7.4 | Requirements Fully Met
M12 | Has a Monitoring & Evaluation Plan been provided that identifies proposed data / performance indicators to monitor against the scheme objectives? | DfT Transport Business Case Guidance - Chapter 6 | 7.3 | Requirements Fully Met
M13 | Are there clear proposals to undertake evaluation of the overall effectiveness of the scheme? | DfT Transport Business Case Guidance - Chapter 6 | 7.9 | Requirements Fully Met