## Summary
INDEPENDENT REVIEW
Project Title: | Crewe Green Roundabout |  | Scheme Promoter: | Cheshire East Council
Document Reviewed: | Transport Business Case |  | Permission Sought: | Full Approval
Date of Submission: |  |  | Date of Review: | 2017-09-20
LEP Accountability Framework:
Scheme Description: | Capacity improvement of the existing Crewe Green Roundabout
SUMMARY SHEET
Overall Score: | 2 |  |  | 1 | Requirements fully met - No issues of note with the submission, project to progress as scheduled.
Overall Comments: | Most of the requirements are covered in all of the cases. There are some minor modelling issues that do not meet full requirements. However this should not preclude the business case from being submitted for full approval. |  |  | 2 | Requirements substantially met - Minor issues exist with the submission. Project to progress and issues to be resolved.
|  |  |  | 3 | Requirements partially met - Medium issues exist with the submission. Project to progress and issues to be resolved urgently.
|  |  |  | 4 | Requirements not met - Critical issues exist with the submission. Project to be suspended whilst issues are resolved.
Case | Status | WSP Comments
Strategic Case | 1 | All main elements are covered.
Economic Case | 2 | The requirements are either fully or substantially met for most aspects. Where requirements are not met it is relatively minor, use of NTEM6.2 for forecasting and lack of micro-simulation input to the strategic model. Given the size of the BCR (now 11.5) these issues can be accepted as not likely to change the value for money category (very high) of the scheme.
Financial Case | 1 | All main elements are covered.
Commercial Case | 1 | All main elements are covered.
Management Case | 1 | All main elements are covered.
Sign-Off
Reviewer's Signature: | 1 |  | Date: | 2017-09-20

## Strategic Case
INDEPENDENT REVIEW
Project Title: |  |  |  | Crewe Green Roundabout
Permission Sought: |  |  |  | Full Approval |  | Date of Review: | 2017-09-20
STRATEGIC CASE
Overall Score |  |  |  | 1 |  |  | 1 | Requirements fully met - No issues of note with the submission.
WSP Comments: |  |  |  | All main elements are covered. |  |  | 2 | Requirements substantially met - Minor issues exist with the submission.
[7 empty] | 3 | Requirements partially met - Medium issues exist with the submission.
[7 empty] | 4 | Requirements not met - Critical issues exist with the submission.
Ref | Item | Applicable Guidance | Key relevant sections in Business Case | FBC Status | Comments |  |  |  | FBC Update Made (report version WD1) | FBC WSP Comment on report version WD1 | Additional FBC Update Made (final LEP submission version Rev3)
S1 | Is there a clear description of the components of the scheme and how it fits with the aims and objectives of the LEP, Local Authorities and DfT? | DfT Transport Business Case Guidance - Chapter 2 | 2.2, 2.3 | Requirements Fully Met | The scheme addresses a significant traffic congestion bottle-neck in the town and thus fits with the aims and objectives of the local authority, the LEP / LTB and DfT objectives.
S2 | Have the problem(s) the scheme will be addressing been clearly identified – including evidence of the extent of the problem(s), specific barriers / challenges, and how the scheme will overcome them (including the scale of impact) | DfT Transport Business Case Guidance - Chapter 2 | 2.2, 2.3 | Requirements Fully Met | The problems to be addressed by the scheme are clearly set out along with the scale of the existing problems. Journey times with and without the scheme are provided in Table 2-12, which demonstrate the scale of time savings. These are presumably across the existing junction, though some are upwards of 5mins in DM. These should be defined (text or map) or they may be more meaningful if they were longer journey routes, e.g. M6 J17 to Crewe, Radway Green to Crewe, Leighton West to A500. |  |  |  | A map showing the start and end points of the journey time routes has been provided in Figure 2-12. | Journey Route now defined by insertion of map with start and end points (Fig2-12)
S3 | Has the impact of not progressing the scheme been set out, including supporting evidence? Is there adequate rationale to support why the scheme is needed now? | DfT Transport Business Case Guidance - Chapter 2 | 2.4 and Table 2-11 | Requirements Fully Met | See comment for S2. What does the DM mean for major traffic flows in Crewe. How does DM 2019 and 2034 compare to base year / current conditions? |  |  |  | Current traffic conditions are provided in terms of journey speeds approaching the junction in Figure 2-4 to 2-6. | Still would be worth an explanation of the impact of DM in 2019 and 2034 and how that compares to current. TM plots (2-4 to 2-6) show current situation, how much worse will that get without the scheme? | Table 2-12 updated to include comparison of future year journey times (both with and without the scheme) to the existing situation (from 2013 base year model). Additional explanatory text also provided.
S4 | Is there a set of specific, measurable, achievable, realistic, time-bound (SMART) objectives for the scheme to address the problem(s) identified? | DfT Transport Business Case Guidance - Chapter 2 | 2.5, 2.6 | Requirements Fully Met | 2.6 outlines some scheme objectives. Journey time savings on what routes (Fig3.4 in Modelling note)? Between what origin and destination? Do they need to be quantified and time measurable? |  |  |  | "Measures for Success" in Section 2.6 updated to quantify desired journey time savings | Are these realistic? Some are -2mins from DM.
S5 | Are the expected outcomes clear - How will it be possible to know when the objectives have been met, and what will ‘success’ actually mean? | DfT Transport Business Case Guidance - Chapter 2 | 2.5, 2.6 | Requirements Fully Met | as S4 above. |  |  |  | See above | As above
S6 | Is it clear what the project is expected to deliver on the ground, including what is in scope and what is out of scope? | DfT Transport Business Case Guidance - Chapter 2 | 1.3, 2.7, Appendix S1 | Requirements Fully Met | 1.3 outlines the key elements of the scheme and modification made to the existing junction layout. A scheme drawing is provided in S1. The scope is summarised in 2.7. What additional information is there in the TA supporting the planning application? Has it been incorporated into the BC? |  |  |  | Section 1.3 has been updated with additional detail about the scheme, including the types of crossings on each arm. Scheme drawing has been updated with the final design (S1). All information in the TA is in line with the information in this business case.
S7 | Have any high-level constraints affecting the ability of the scheme to solve the problem(s) been identified? | DfT Transport Business Case Guidance - Chapter 2 |  | Not Applicable | No such constraints have been identified.
S8 | Have any interdependencies which may affect the success of the scheme been identified? | DfT Transport Business Case Guidance - Chapter 2 | 2.9 | Requirements Fully Met | The main inter-dependency relate to the Sydney Road Bridge scheme. Both these scheme need to be programmed for delivery sequentially due to the road closures and diversionary routes that need to be implemented. This has been taken into account in developing the scheme programme.
S9 | Have relevant studies and technical work that has informed the development of the scheme been identified? |  | 2.5, 2.6, Appendix S4, S5 | Requirements Fully Met | Is there a toucan crossing on Hungerford Road? This is not detailed in section 1.3. Safety will obviously have been a consideration in the design process, can interaction with NMU groups mentioned in the assurance meeting be documented? Ultimately the Road Safety Audit is a pressing need for this scheme. |  |  |  | Section 1.3 has been updated with additional detail about the scheme, including the types of crossings on each arm. A Road Safety Audit has been undertaken. Following its recommendations, CEC are looking into reducing some speed limits on approach to 30mph. | Can the RSA be included the appendix? | RSA and designers response included as Appendices S7 and S8
S10 | Are any links with other schemes clear and has the 'in-combination' impact been considered? | DfT Transport Business Case Guidance - Chapter 2 | 2.9 | Requirements Fully Met | Whilst there is an inter-dependency between this scheme and the Sydney Road Bridge scheme in terms of construction sequencing, the two schemes are independent and hence an i-combination impact is not considered necessary.
S11 | Have the main stakeholder groups and their contribution to the project been defined? This should include any potential conflicts between different stakeholder groups and their demands. | DfT Transport Business Case Guidance - Chapter 2 | Appendix S2 | Requirements Fully Met | The stakeholder groups have been identified and mapped. No significant conflict between groups has been identified.
S12 | Is there a robust assessment of different scheme options, including the reasons for any options being discounted? Has an EAST options appraisal been undertaken? | The Transport Appraisal Process | 2.11 | Requirements Fully Met | Four alternative options have been considered, assessed and put to stakeholder and public consultation. An EAST type appraisal was undertaken against seven key scheme requirements.
S13 | Have details of stakeholder and public consultation been provided? | DfT Transport Business Case Guidance - Chapter 2 | 2.10 and Appendices S2, S3 and S4 | Requirements Fully Met | Detailed information on stakeholder and public consultation is included along with a report on the consultation responses.

## Commercial Case
INDEPENDENT REVIEW
Project Title: |  |  |  | Crewe Green Roundabout
Permission Sought: |  |  |  | Full Approval |  | Date of Review: | 2017-09-20
COMMERCIAL CASE
Overall Score |  |  |  | 1 |  |  | 1 | Requirements fully met - No issues of note with the submission.
WSP Comments: |  |  |  | All main elements are covered. |  |  | 2 | Requirements substantially met - Minor issues exist with the submission.
[7 empty] | 3 | Requirements partially met - Medium issues exist with the submission.
[7 empty] | 4 | Requirements not met - Critical issues exist with the submission.
Ref | Item | Applicable Guidance | Key relevant sections in Business Case | FBC Status | Comments |  |  |  | FBC Update Made (report version WD1) | FBC WSP Comment on report version WD1 | Additional FBC Update Made (final LEP submission version Rev3)
C1 | Has a robust procurement strategy been clearly set out? | DfT Transport Business Case Guidance - Chapter 5 | 5.3 | Requirements Fully Met | Yes, the Scape framework is to be used to procure the construction of the scheme. The output based specification is included
C2 | Has consideration of different procurement options been demonstrated, including justification for selection of the preferred option? | DfT Transport Business Case Guidance - Chapter 5 | 5.3 | Requirements Fully Met | Yes, OJEU procurement, Highways England's Collaborative Delivery Framework and the Scape Framework considered.
C3 | Have the proposed payment mechanisms / pricing framework been identified? | DfT Transport Business Case Guidance - Chapter 5 | 5.4 | Requirements Fully Met | NEC 3 Target Cost Contract selected.
C4 | Have the procurement timescales been set out, and are they realistic? | DfT Transport Business Case Guidance - Chapter 5 | 5.6 | Requirements Fully Met | Yes, appointment is expected in January 2018 and given that this will be through the Scape Framework then the timescales are realistic.
C5 | Have details of the proposed risk transfer / allocation been provided? | DfT Transport Business Case Guidance - Chapter 5 | 5.5 and 6.11 of Management Case | Requirements Fully Met | A single, jointly-owned risk register has been developed and a Quantified Risk Assessment workshop has been held. Each risk is allocated an owner. The risk register will be a live document and be continually reviewed and updated. An opportunities register has also been developed. A copy of the risk register is included within the Management Case. |  |  |  | The risk register has been updated with the latest vesrion and is included as appendix M3. The top risks have been updated in table 6.5.
C6 | Have details of contract management been provided, including contract timescales? | DfT Transport Business Case Guidance - Chapter 5 | 5.6 | Requirements Fully Met | The contract timescales are provided with start of works planned for January 2018 with works complete by November 2018. A period of 8 weeks float has been allowed at the end of the submitted programme. Whilst a detailed programme has not been included, the timescales appear reasonable for the scale of the project. |  |  |  | Revised programme included as appendix M2. | Noted. Highway works still to complete in November 2018
C7 | Has evidence of relevant approval been provided from Head of Procurement? | DfT Transport Business Case Guidance - Chapter 5 | 1.4 | Requirements Fully Met | There is no evidence provided of approval from the Head of Procurement, although the document states that the procurement strategy was approved by the CEC Cabinet on18 October 2016. Evidence should be included. |  |  |  | Meeting minutes from the CEC Cabinet meeting on 18 October 2016 have been included as Appendix C2. | Item 51 of minutes provides evidence of approval of preferred option and approval of procurement by the cabinet. Is there any further evidence referencing the Head of Procurement? Ultimately if CEC are staisified with this as evidence then it should be sufficient. | Email from Corporate Procurement at Cheshire East Council forwarded to assurance team

## Management Case
INDEPENDENT REVIEW
Project Title: |  |  |  | Crewe Green Roundabout
Permission Sought: |  |  |  | Full Approval |  | Date of Review: | 2017-09-20
MANAGEMENT CASE
Overall Score |  |  |  | 1 |  |  | 1 | Requirements fully met - No issues of note with the submission.
WSP Comments: |  |  |  | All main elements are covered. |  |  | 2 | Requirements substantially met - Minor issues exist with the submission.
[7 empty] | 3 | Requirements partially met - Medium issues exist with the submission.
[7 empty] | 4 | Requirements not met - Critical issues exist with the submission.
Ref | Item | Applicable Guidance | Key relevant sections in Business Case | FBC Status | Comments |  |  |  | FBC Update Made (report version WD1) | FBC WSP Comment on report version WD1 | Additional FBC Update Made (final LEP submission version Rev3)
M1 | Has the proposed governance / organisational structure been provided? Does it provide a robust means of overseeing project delivery with appropriate skills / experience? | DfT Transport Business Case Guidance - Chapter 6 | 6.4 | Requirements Fully Met | A clear governance structure is in place with a named Senior Responsible owner and a project board to oversee the implementation of the project. Monthly project board meetings have been taking place.
M2 | Does the project programme demonstrate realistic delivery timescales? Does it provide an appropriate level of detail, eg in GANTT chart form? | DfT Transport Business Case Guidance - Chapter 6 | 6.5 | Requirements Fully Met | A detailed project programme is provided and the project timescales are realistic for a project of this scale. |  |  |  | Revised programme included as appendix M2. | Noted
M3 | Have critical path items and dependencies been clearly identified? | DfT Transport Business Case Guidance - Chapter 6 | 6.5 | Requirements Fully Met | Project dependencies are set out and the critical path activities are detailed in the programme in appendix M2. |  |  |  | The schemes project dependencies have been updated as per the current situation. | Noted
M4 | Have required statutory powers and consents been identified, including current status and timescales for obtaining these powers if they are not already in place? | DfT Transport Business Case Guidance - Chapter 6 | 6.5 | Requirements Fully Met | Details are provided along with their current status and timescales for securing these approvals/powers.
M5 | Have details of the reporting, assurance and approval process been provided (including gateways in scheme development / delivery)? | DfT Transport Business Case Guidance - Chapter 6 | 6.6 | Requirements Fully Met | The Council's established 'Project Gateway' procedure is being used for this project which involves governance through a Member led Executive Management Board.
M6 | Has evidence of scheme delivery been provided, to demonstrate that the delivery body has the capability and means to successfully implement the scheme? | DfT Transport Business Case Guidance - Chapter 6 | 6.2 | Requirements Fully Met | The Council has a successful track record of delivery of other major highways schemes of much higher value and so we are confident that it has the capability and means to successfully implement this scheme.
M7 | Has a Risk Management Strategy been provided, setting out how risks have been identified, their likely impact, appropriate mitigation, and how the risks will be managed (and by whom)? | DfT Transport Business Case Guidance - Chapter 6 | 6.11 | Requirements Fully Met | A risk management strategy is in place and a detailed risk register has been produced identifying likely impacts and mitigation measures. A 'risk owner' has been allocated to manage each risk. |  |  |  | The date of the most recent review of the risk register has been updated | Noted
M8 | Have key risks been identified and are suitable mitigation measures proposed? | DfT Transport Business Case Guidance - Chapter 6 | 6.11 | Requirements Fully Met | The key risks have been identified with suitable mitigation measures proposed for these. |  |  |  | The key risks have been updated to reflect the most recent updates to the risk register. Updated risk register included as Appendix M3. | Noted
M9 | Is there a Stakeholder Management Plan that identifies key stakeholders and details how engagement / consultation will be undertaken? | DfT Transport Business Case Guidance - Chapter 6 | 6.7 and 2.1, Appendix S2 of the Strategic Case | Requirements Fully Met | A Stakeholder Management Strategy/Plan has been developed identifying the key stakeholders and how engagement / consultation will be / has been undertaken. A detailed consultation report is included as an appendix to the Strategic Case.
M10 | Does the scheme have support? Is it likely to be acceptable? | DfT Transport Business Case Guidance - Chapter 6 | 6.7 and 2.1, Appendix S3 of the Strategic Case | Requirements Fully Met | Stakeholder and public consultation has been undertaken in selecting between the various improvement options. There is clear support for the preferred option.
M11 | Is there a clear intervention logic for how the outcomes will be achieved? (e.g. logic map) | DfT Transport Business Case Guidance - Chapter 6 | 6.12 | Requirements Fully Met | A benefits realisation plan has been included along with a logic map showing how the expected outcomes will be achieved.
M12 | Has a Monitoring & Evaluation Plan been provided that identifies proposed data / performance indicators to monitor against the scheme objectives? | DfT Transport Business Case Guidance - Chapter 6 | 6.12 and Appendix M4 | Requirements Fully Met | A Monitoring and Evaluation Plan has been provided. The scheme will be subject to the DfT's Standard Monitoring requirements and details of the data to be collected against the scheme objectives has been included. Targets have been included in table 1-6, though some targets are yet to be quantified (e.g. percentage JT savings on which route). |  |  |  | Table 7-1 of the Benefis Realisation Plan have been updated to include the quantification of journey time saving targets, based on the anticipated travel times derived through traffic modelling. Definition of the journey time routes that should be monitored (including start and end points) have been included. Table 6.6 in Management Case similarly updated. | As S4, are these realistic? Some are -2mins from DM.
M13 | Are there clear proposals to undertake evaluation of the overall effectiveness of the scheme? | DfT Transport Business Case Guidance - Chapter 6 | 6.12 and Appendix M4 | Requirements Fully Met | As per M12 above. |  |  |  | As per M12 above

## Economic Case
INDEPENDENT REVIEW
Project Title: |  |  |  | Crewe Green Roundabout
Permission Sought: |  |  |  | Full Approval |  | Date of Review: | 2017-09-20
ECONOMIC CASE
Overall Score |  |  |  | 2 |  |  | 1 | Requirements fully met - No issues of note with the submission.
WSP Comments: |  |  |  | The requirements are either fully or substantially met for most aspects. Where requirements are not met it is relatively minor, use of NTEM6.2 for forecasting and lack of micro-simulation input to the strategic model. Given the size of the BCR (now 11.5) these issues can be accepted as not likely to change the value for money category (very high) of the scheme. |  |  | 2 | Requirements substantially met - Minor issues exist with the submission.
[7 empty] | 3 | Requirements partially met - Medium issues exist with the submission.
[7 empty] | 4 | Requirements not met - Critical issues exist with the submission.
Ref | Item | Applicable Guidance | Key relevant sections in Business Case | FBC Status | Comments |  |  |  | FBC Update Made (report version WD1) | FBC WSP Comment on report version WD1 | Additional FBC Update Made (final LEP submission version Rev3)
E1 | Has a Value for Money Statement been provided, including a BCR? | TAG Unit A1.1 – Cost Benefit Analysis | 7.2 | Requirements Fully Met | PVB, PVB, NPV and BCR are clearly stated in 2010 prices discounted to 2010. The BCR is 9.8 placing the scheme in the very high value for money category |  |  |  | PVC, NPV and BCR updated based on latest scheme costs. | BCR now at 11.5
E2 | Are there any key assumptions relating to how the BCR has been derived? | TAG Unit A1.1 – Cost Benefit Analysis | 2 & 3, EAR | Requirements Fully Met | All key assumptions are clearly stated in EC and EAR. Following TAG 60 appraisal of benefits using latest versions of TUBA and COBA-LT. Change in travel time and distances from a local SATURN model. |  |  |  |  | An updated version of TUBA, v1.9.9, has been released. This reflects the latest TAG data book, v1.8.1 July 2017. | Sentence added to EAR Sec2.3 to justify use of TUBA v1.9.8 rather than v1.9.9: "Shortly prior to the final submission of the Business Case, a new version (1.9.9) of TUBA was released, reflecting slight updates to the forecast values of time. Given the short timescales available, and the fact that the new version of TUBA would not materially affect the value for money conclusion of the scheme, the analysis was not updated to incorporate this new release."
Benefits
E3 | Is the basis for the calculation of the Present Value of Benefits (PVB) sufficiently robust? Has sufficient information been provided on how this has been derived? | TAG Unit A1.1 – Cost Benefit Analysis | 2, EAR | Requirements Fully Met | The PVB calculation methodology is well set out. Opening year and forecast year used for 60 year appraisal. All benefits in 2010 prices discounted to 2010.
Costs
E4 | Is the basis for the calculation of the Present Value of Cost (PVC) sufficiently robust? Has sufficient information been provided on how this has been derived? | TAG Unit A1.2 – Scheme Costs | 4.2 and FC 1.2 | Requirements Fully Met | Costs have been developed in 2016 prices. Inflation has been applied to bring in line with the spend profile, optimism bias and risk has been added and sunk costs removed. Costs have then been converted to 201 prices and discounted to 2010. |  |  |  | PVC updated based on latest scheme costs. No change to methodology from CABC. | Noted
E5 | Has an appropriate level of optimism bias been applied? |  | 4.1 | Requirements Fully Met | OB at 15% has been applied which is appropriate at this stage |  |  |  | OB updated to 3% as per TAG guidance for Full Business Case stage | Noted
E6 | Has an appropriate level of risk cost been included? |  | 4.1 | Requirements Fully Met | Risk is stated at being 7% of scheme cost with a QRA completed. Top 5 risks are included in the FC, Risk Register as an appendix to MC. |  |  |  | Risk amount and Top 5 risks updated following QRA update | Noted
Modelling, Forecasting & Economic Analysis
E7 | Is the traffic modelling and forecasting approach / tools sufficiently robust? | TAG Unit A5.5 – Highway Appraisal | 3.2, TFR addendum, Supplementary Modelling Technical Note. | Requirements Substantially Met | The approach to modelling is fixed demand forecasting in a strategic highway only model. Fuel and Income growth has been applied. A stand alone junction model has been developed in Junctions 9 to assist in calibrating the SATURN model. This is a sensible approach. It appears it has been modelled as a roundabout within Junctions 9. Given the relatively unique design (6 arms, lozenge shape, ICD up to 150m+) is this better than using micro-sim? NTEM6.2 has been used as the basis for car forecasting. A comparison of car driver growth factors has been provided for NW region between NTEM6.2 and NTEM7.2. This shows that NTEM6.2 over predicts the growth to 2019 by 3%. This will result in over prediction of the PVB between 2019 and 2033 inclusive. The addendum list the developments that have been explicitly modelled. The TRF states that these developments can all be considered to be "Near Certain" or "More Than Likely" |  |  |  | Given programme pressures, a decision was made during the ASR development not to undertake VISSIM modelling, or update forecast SATURN models in line with NTEM 7.2. | Comment as before
E8 | Have all other modelling assumptions been made clear? | TAG Unit M1.1 – Principles of Modelling and Forecasting | 3.2, EAR | Requirements Fully Met | How are the toucan crossing modelled within SATURN and Junctions 9? |  |  |  | No allowance has been made for toucan crossings in the traffic models. This was considered suitable given the low level of NMU demand. | Is this based upon actual data, i.e. NMU surveys across the junction. | A summary of NMU counts on all crossings at the junction are provided in the worksheet "Supporting info - NMU Counts" as part of this assurance spreadsheet. It can be seen that NMU numbers are low. The total number of incidents where the crossings are activated are likely to be even lower than this (given that multiple NMUs are likely to cross together at times).
E9 | Has relevant supporting documentation been provided to substantiate that modelling undertaken is fit for purpose? (e.g. data / traffic surveys report, LMVR, Forecasting Report) | TAG Unit M3.1 – Highway Assignment Modelling | TFR Addendum | Requirements Fully Met | A suite of supporting documentation for modelled has been provided - LMVR, TFR, TFR Addendum, Supplementary Modelling Technical Note, and EAR.
E10 | Are TUBA outputs robust? | TAG Unit M4 – Forecasting and Uncertainty | EAR | Requirements Fully Met | The TUBA results have been filtered by sector in order to remove any benefits due to changes in the buffer and external network. Benefits are considered within 7 sectors and a sector map has been provided. A time benefits by sector matrix is included. Commentary on the sector to sector benefits is provided, relief of CGR congestion has benefits all over Crewe, this is further backed up by the diff plots included in Supplementary Modelling Technical Note. EAR3 shows that PM 2034 produces the lowest time benefit. It would be instructive to understand why the scheme's performance tails off in the PM peak, given that even accounting for annualisation the PM 2019 time benefit is bigger than AM 2034. Some commentary is provided stating that it is "a result of high PM traffic demand within the 2034 assessment year limiting congestion relieving benefits offered by the scheme". Given the change from 2019 PM benefits, this may be due to location of developments and development traffic rather than background growth. |  |  |  | No updates made either to SATURN modelling or text relating to benefits. | Comment as before | Typo corrected in EAR Sec7.1 (NPV updated to £53.4m).
E11 | Have all relevant options been modelled / appraised? | TAG Unit M2 – Variable Demand Modelling | 2.4 | Requirements Fully Met | Only the preferred option is being assessed.
E12 | Have appropriate sensitivity tests been undertaken? | TAG Unit A1.3 – User and Provider Impacts | 2.5 | Requirements Fully Met | Previously agreed with C&W LEP that scheme cost meant a proportionate approach and no growth or cost sensitivity tests to be undertaken.
Scheme Impacts
E13 | Has a completed AST been provided (with supporting worksheets where relevant)? | Guidance for the Technical Project Manager | E-2 | Requirements Fully Met | Supporting worksheets for Environmental and Social Benefits are appended.
E14 | Has sufficient justification been provided on scoping out of any specific impacts? | Guidance for the Technical Project Manager | 2.2 | Requirements Fully Met | All impacts scoped out have been listed.
E15 | Has sufficient justification been provided on the approach used to appraise each impact (e.g. quantitative / qualitative)? | Guidance for the Technical Project Manager | 2.1, 5, 6 | Requirements Fully Met | The split between quantitative and qualitative seems reasonable for a scheme of this scale.
E16 | Have all (relevant) Economic Impacts been adequately assessed and are the ratings (seven-point scale) reasonable? | TAG Unit A1.3 – User and Provider Impacts | E-2 | Requirements Fully Met | Only regeneration using seven point scale. Neutral seems reasonable rating
TAG Unit A2.1 – Wider Impacts
TAG Unit A2.2 – Regeneration Impacts
E17 | Are forecast housing, jobs and GVA impacts provided robust / realistic? |  |  | Not Applicable
E18 | Have all (relevant) Environmental Impacts been adequately assessed and are the ratings (seven-point scale) reasonable? | TAG Unit A3 – Environmental Impact Appraisal | 6.3, E-2 | Requirements Fully Met | The ratings seem reasonable given that it is a junction upgrade with a small amount of and take. Completed worksheets have been provided.
E19 | Have key environmental constraints been clearly identified? | TAG Unit A3 – Environmental Impact Appraisal |  | Not Applicable
E20 | Have all (relevant) Social Impacts been adequately assessed? and are the ratings (seven-point scale) reasonable? | TAG Unit A4.1 – Social Impact Appraisal | 6.4, E-2 | Requirements Fully Met | Worksheets have been provided. Ratings seem reasonable, Severance to be corrected to neutral in AST. The impact of accidents should be RSA led. RSA have been commissioned |  |  |  | RSA has been undertaken. Reference made to this in the strategic case section 1.3. No change to the monetisd COBALT assessment has been made based on RSA. | Severance still categorised as Slight Beneficial in table 3-5 though modified in the AST. | Severance score updated to 'neutral' in Table 3-5 and Section 3.6.4.
E21 | Have Distributional Impacts been assessed in a robust manner? | TAG Unit A4.2 – Distributional Impact Appraisal |  | Not Applicable

## Financial Case
INDEPENDENT REVIEW
Project Title: |  |  |  | Crewe Green Roundabout
Permission Sought: |  |  |  | Full Approval |  | Date of Review: | 2017-09-20
FINANCIAL CASE
Overall Score |  |  |  | 1 |  |  | 1 | Requirements fully met - No issues of note with the submission.
WSP Comments: |  |  |  | All main elements are covered. |  |  | 2 | Requirements substantially met - Minor issues exist with the submission.
[7 empty] | 3 | Requirements partially met - Medium issues exist with the submission.
[7 empty] | 4 | Requirements not met - Critical issues exist with the submission.
Ref | Item | Applicable Guidance | Key relevant sections in Business Case | FBC Status | Comments |  |  |  | FBC Update Made (report version WD1) | FBC WSP Comment on report version WD1 | Additional FBC Update Made (final LEP submission version Rev3)
F1 | Is the expected whole life cost of the scheme robust, including the base cost and risk allowance in out-turn prices drawn from industry forecasts? | TAG Unit A1.2 – Scheme Costs | 1.2 - 1.7 | Requirements Fully Met | Costs have been developed by CEC, including input from construction contractor Balfour Beatty. These are in 2016 prices. The costs do not quantify operation and maintenance costs as agreed with C&W LEP. An allowance for risk has been made, informed by a quantified risk assessment. The actual values used for inflation are not given, but the source of inflation values for each cost type are stated. |  |  |  | Scheme costs updated based on final target costs received from construction contractor Balfour Beatty in Sept 2017. | Noted
F2 | Has a cost profile been provided showing year on year costs, and breakdown by cost type and parties on whom they fall? | DfT Transport Business Case Guidance - Chapter 4 | 1.6, F-1 | Requirements Fully Met | A cost profile has been provided, showing costs from 2017 to 2019. |  |  |  | Cost profile updated | Noted
F3 | Have details of key financial risks been provided and is the risk cost allowance robust? | TAG Unit A1.2 – Scheme Costs | 1.3, 1.4 | Requirements Fully Met | A quantified risk assessment has been undertaken. £0.43m risk has been identified. The top five risks are stated, though there is no costs or risk category associated with them. A risk register is included in the MC. No monetary value has been stated for any of the risks. No QRA report is included in the BC documentation. Contingency is also included in the cost elements, to a total of £0.11m |  |  |  | Costs updated based on latest update to QRA / Contingency allowance. Updated risk register included in Appendix M3. | Individual risk costs not presented. | Appendix M3 updated to show costs for individual risks. Section 4.3 of Financial Case updated to show "Top Six" risks based on these individual risk costs.
F4 | Are funding sources to cover the full scheme cost clearly set out? | DfT Transport Business Case Guidance - Chapter 4 | 1.8 | Requirements Fully Met | Funding is from LGF (3.3), NPIF (1.95) and CEC (2.17, of which 1.7 to come from S106. Forward funding approved April 2017)
F5 | Is there sufficient evidence to support third party / alternative funding contributions? | DfT Transport Business Case Guidance - Chapter 4 | 1.8 | Requirements Fully Met | Forward funding for S106 has been approved. Information is provided on what developments will be contributing to the s106 payments.
F6 | Have the impacts of third party / alternative funding not coming forward been considered? | DfT Transport Business Case Guidance - Chapter 4 | 1.8 | Requirements Fully Met | Forward funding for S106 has been approved. CEC has approved the underwriting of any funding gap.
F7 | Has the the long-term financial sustainability of the scheme been demonstrated, including robust plans to ensure the affordability of any ongoing costs for operation, maintenance and major capital renewals? | TAG Unit A1.2 – Scheme Costs | 1.7 | Requirements Fully Met | The costs do not quantify operation and maintenance costs as agreed with C&W LEP.
F8 | Has evidence of appropriate S151 Officer sign-off been provided? |  |  | Not Applicable