## Sheet1
LGF projects - Key Milestones for publicity
|  | 17/18 | [11 empty] | 18/19
|  | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March
Project | Activity
Sydney Road Bridge | Conditional Offer Letter issued
Planning approved
Project Starts on site
Project finishes
Crewe Green Roundabout | Conditional Offer Letter issued
Planning approved
Project Starts on site
Project finishes
Chester Central | Official opening
OMEGA - Birchwood Pinchpoint
M & Cheshire Life Science Investment Programme | First £1m invested?
Reaseheath Agri Tech Centre
Reaseheath Learning Hub and Accommodation
Reaseheath Employer Focused Hub
Reaseheath Sports Science and Performance Academy
Thornton Science Park | First tennants move in
Cheshire and Warrington Growth Hub
M62 J8 Junction Improvements
Warrington Waterfront (Centre Park Link) | Offer letter issued
Warrington West Station | Offer letter issued
Start on site
Ellesmere Port Central Development Zone
Poynton Relief Road
Crewe High Growth City – Congleton Link Road
Reaseheath Additional Accomodation | Conditional offer letter
West Cheshire College
LGF3 projects??
Crewe Ready Heart
Growing Places Fund
Cheshire Green
Jodrell Bank
AMRC

## All projects
Date updated: | 2020-08-27
Project | Total project cost (£) | Intevention rate (%) | Total grant | Paid in 15/16 | Paid in 16/17 | Paid in 17/18 | Actual Q1 17/18 | Actual Q2 17/18 | Actual q3 17/18 | Actual q4 17/18 | Paid to date | Profiled 18/19 | Profiled Q1 18/19 | Actual q1 18/19 | Profiled Q2 18/19 | Actual q2 18/19 | Profiled Q3 18/19 | Actual q3 18/19 | Actual q3 18/19 | Profiled Q4 18/19 | 19/20 | 20/21 | Total | Comment
LGF1/2
BEIS funding Profile |  |  |  | 14520000 | 45787235 | 7920938 | [5 empty] | 7521336 | [8 empty] | 3990092 | 4712629 | 84452230
Balance c/f (defrayed by CEC) |  |  |  | 0 | 0 | 19718528.27 | [5 empty] | 19744168.46 | [8 empty] | 14835307.745 | 1255323.82
Total Balance (profile +c/f) |  |  |  | 14520000 | 45787235 | 27639466.27 | [5 empty] | 27265504.46 | [8 empty] | 18825399.745 | 5967952.82
Completed Projects
Chester Central | 21637682 | 62.3912 | 13500000 | 6287993 | 7212007 | 0 | 0 | 0 |  |  | 13500000 | 0 | [8 empty] | 0 |  | 13500000
Thornton Science Park | 17382850 | 39.119 | 6800000 | 2500000 | 4300000 | 0 |  |  |  |  | 6800000 | [11 empty] | 6800000
Housing Fund Revenue (CWAC) | 7500000 | 100 | 7500000 | 7500000 | [6 empty] | 7500000 | [11 empty] | 7500000
DfT Tail majors including Crewe Green Link Road | 25747350 | 18.6427 | 4800000 | 4800000 | [6 empty] | 4800000 | [11 empty] | 4800000
Birchwood Pinchpoint | 4986000 | 42.9202 | 2140000 | 2140000 | 0 | 0 | 0 | 0 |  | 0 | 2140000 | [11 empty] | 2140000
M62 J8 Junction Improvements (Omega) | 11690000 | 42.7716 | 5000000 |  | 2476986 | 2523014 | 1660000 |  | 363014 | 500000 | 5000000 | 0 |  | 0 |  | 0 | [6 empty] | 5000000 | Fully claimed
Reaseheath Agri Tech Centre | 7457971.56 | 33.186 | 2475000 | 835000 | 1069000 | 447250 |  | 323500 | 0 | 123750 | 2351250 | 123750 |  | 0 | 123750 | 123750 |  |  |  | 0 |  |  | 2475000 | Fully claimed
Reaseheath Employer Focused Hub | 1889306.55 | 35.7195 | 674850 | 41000 | 412000 | 188107.5 |  | 50193 | 104172 | 33742.5 | 674850.5 | 33742.5 | 33743 | 0 | 33742 | 33743 |  |  |  | 0 |  |  | 674850.5 | Fully claimed
Reaseheath Sports Science and Performance Academy (osprey) | 6169153.63 | 35.171 | 2169750 | 330000 | 1179000 | 552262.5 |  | 443775 | 0 | 108487.5 | 2169751 | 108488 |  | 0 | 108488 | 108488 | [6 empty] | 2169750 | Fully claimed
Ellesmere Port and Chester Campus remodelling | 3791198 | 84.3533 | 3198000 |  | 0 | 955796.61 |  | 546425 | 0 | 409371.61 | 3198000 | 2242203.39 |  | 1175820.68 | 0 | 1066382.71 |  |  | 0 | 0 |  |  | 3198000 | Complete
Live Projects
Sydney Road Bridge | 10378000 | 56.3692 | 5850000 |  | 800000 | 1367646 | 530646 | 115000 | 105000 | 617000 | 3019846 | 2830154 |  | 113000 | 163000 | 675200 | 500000 |  | 64000 | 1378954 | 0 |  | 5850000 | Profile updated May 18 | 5737000
Crewe Green Roundabout | 7500000 | 44 | 3300000 |  | 381480 | 962527 | 962527 | 0 | 0 | 0 | 3300000 | 1955993 | 500000 | 540423 | 500000 | 1103857 | 0 |  | 311713 | 0 |  |  | 3300000 | updated 17.04.18
GM & Cheshire Life Science Investment Programme | 31982000 | 31.2676 | 10000000 | 1459006.52 | 2269701.73 | 3273615.64 |  | 1710097.72 | 1042345.28 | 521172.64 | 7979516.79 | 2188900 | 469050 | 651460 | 625400 |  | 469050 | 325732.9 | 325732.9 | 600000 | 808776 | 0 | 10325732.79 | updated 17.04.18
Reaseheath Learning Hub and Accommodation | 11244158.13 | 31.8593 | 3582315 | 927000 | 1685000 | 791199.5 |  | 612084 | 0 | 179115.5 | 3582315.5 | 152800 | 0 | 0 |  |  |  |  | 179116 |  |  |  | 3582315.5 | 5% left to claim
Warrington Waterfront (Centre Park Link) | 19891000 | 26.6452 | 5300000 |  | 2383532 | 1804104 | 424000 | 0 | 0 | 1380104 | 4770000 | 582364 |  | 0 | 0 | 0 | 0 |  | 582364 | 0 | 530000 |  | 5882364 | Profile updated 06.06.18 dependent on land issues being resolved. Profile reflects funding 100% of costs to date and looks to hold back 10% in final year
Warrington West Station | 19694000 | 33.1573 | 6530000 |  | 1900000 | 3167429 | 665000 | 535000 | 302979 | 1664450 | 5877000 | 809571 | 200000 | 809571 | 0 | 0 | 0 |  | 0 | 0 | 653000 |  | 6530000 | reprofiled 17.04.18 to reflect revised int. rate and need to hold back 10%
Ellesmere Port Central Development Zone | 17392000 | 47.9084 | 8332228 |  |  | 0 |  |  | 0 | 0 | 0 | 285500 |  | 0 |  | 0 | 125000 |  | 0 | 160500 | 2445000 | 5601728 | 8332228 | Profile updated November 18 following OBC submission
Poynton Relief Road | 50700000 | 11.0454 | 5600000 |  | 0 | 0 |  |  | 0 | 0 | 0 | 4000000 |  | 0 |  |  | 0 |  | 0 | 4900000 |  | 1600000 | 5600000 | Updated November 18 based on OBC approvel in Feb 19
Total LGF 1/2 spend | 277032669.87 | 34.9245 | 96752143 | 26819999.52 | 26068706.73 | 16032951.75 | 4242173 | 4336074.72 | 1917510.28 | 5537193.75 | 76662529.79 | 15313465.89 | 1202793 | 3290274.68 | 1554380 | 3111420.71 | 1094050 | 325732.9 | 1462925.9 | 7039454 | 4436776 | 7201728 | 97660240.79
Funding defrayed on CEC projects |  |  |  | 0 | 19718528.27
12073850
LGF3 |  |  | Indicative allocation / Profile
BEIS funding Profile | [5 empty] | 10348178 | 18269116 |  |  |  |  | 8494566 | [8 empty] | 4244678 | 20192577 | 61549115
Crewe High Speed-ready Heart Town Centre Regeneration Programme | 24700000 | 40.4858 | 10000000 |  |  | 480269.06 | 0 | 0 | 177735.67 | 302533.39 | 715141.65 | 720000 | 51250 | 80831.5 | 32000 | 87509.24 | 290800 |  | 66531.85 | 50000 | 5195000 | 3604731 | 10000000.06 | Profile from CEC updated 02.08.18
Unlocking Winsford Industrial expansion Land | 10900000 | 34.8624 | 3800000 | 0 | 0 | 220000 |  |  | 160000 | 60000 | 337540.01 | 997500 |  | 0 | 50000 | 73084.44 | 200000 |  | 44455.57 | 100000 | 1716684 | 865816 | 3800000 | Updated profile on 02.08.18
Tarvin Road | 5427000 | 67.4959 | 3663000 |  |  | 0 |  |  |  | 0 | 157928 | 328116.825 | 121500 | 0 | 67000 | 118715 | 70000 |  | 39213 | 72401.825 | 1817228.925 | 1517654 | 3662999.75 | Based on profile provided April 18. Awaiting reprofile
Warrington East Highways Improvements | 13500000 | 51.1111 | 6900000 |  |  | 1510255 |  |  |  | 1510255 | 2855645.16 | 3540680 | 70200 | 68865.16 | 800000 | 285123 | 900000 |  | 991402 | 900000 | 1849065 | 0 | 6900000 | Updated profile 17.04.18
Omega Local Highways Schemes phase 2 | 6465000 | 66.512 | 4300000 |  |  | 0 |  |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 500000 | 3800000 | 4300000 | updated 11.09.18. needs confirming by WBC
Skills | 5000000 | 100 | 5000000 |  |  | 0 |  |  |  |  | 0 | 0 |  | 0 | 0 |  |  |  | 0 | 0 | 2500000 | 2500000 | 5000000 | Updated Jan 19
Energy Innovation | 4151070 | 100 | 4151070 |  |  | 0 |  |  |  |  | 0 | 0 |  | 0 | 0 |  |  |  | 0 | 0 | 2000000 | 2151070 | 4151070 | Updated Jan 19
Joint Cheshire and Warrington Sustainable Travel Access Fund | [5 empty] | 0 |  |  |  |  | 0 | 0 |  | 0 | 100000 |  | 0 |  | 0 | 0 | 0 | 0 | 0
Burtonwood Omega Path (WBC) | 1000000 | 50 | 500000 | [7 empty] | 0 | [5 empty] | 0 |  | 0 | 15000 | 0 | 500000 | 500000 | CPO process underway. Profile updated Jan 19
Chester Road (WBC) | 900000 | 66.6667 | 600000 | [7 empty] | 0 | [7 empty] | 0 |  | 200000 | 400000 | 600000 | seeking full approval Dec 18
TPT Upgrade (WBC) | 900000 | 66.6667 | 600000 | [7 empty] | 0 | [7 empty] | 0 |  | 0 | 600000 | 600000 | Estimated profile updated jan 19
Wilmslow Strategic Cycle and Walking route (CEC) | 1300000 | 38.4615 | 500000 | [7 empty] | 0 | [7 empty] | 0 |  | 0 | 500000 | 500000 | Seeking full approval mar 19
Northwest Crewe Cycling and Walking Link (CEC) | 2145000 | 51.2821 | 1100000 | [7 empty] | 0 | [7 empty] | 0 |  | 1100000 |  | 1100000 | Seeking full approval mar 19
A5117 Cycle Route, Ellesmere Port (CWAC) | 602000 | 63.1229 | 380000 | [7 empty] | 0 | [7 empty] | 0 |  | 100000 | 280000 | 380000 | Estimated profile
Station View and Canal Towpath (CWAC) | 4379000 | 15.5287 | 680000 | [7 empty] | 0 | [7 empty] | 0 |  | 200000 | 480000 | 680000 | Estimated profile
Sutton Way Boulevard, Ellesmere Port (CWAC) | 1024000 | 62.5 | 640000 | [7 empty] | 0 | [7 empty] | 0 |  | 200000 | 440000 | 640000 | Estimated profile
Macclesfield College - Chef's Whites Academy | 200000 | 12.5 | 25000 |  |  | 0 |  |  |  |  | 13275.05 | 25000 |  | 0 |  | 10585.66 |  |  | 2689.39 | 14414 | 0 | 0 | 25000
Total LGF3 Spend | 82593070 | 51.8676 | 42839070 | 0 | 0 | 2210524.06 | 0 | 0 | 337735.67 | 1872788.39 | 4079529.87 | 5611296.825 | 242950 | 149696.66 | 1049000 | 575017.34 | 1460800 | 0 | 1144291.81 | 1151815.825 | 17377977.925 | 17639271 | 42839069.81
Difference between profile and forecast spend | [5 empty] | 8137653.94 | [14 empty] | -13133299.925 | 2553306
LGF total profile | [5 empty] | 18269116 | [5 empty] | 16015902 | [8 empty] | 8234770 | 24905206
TotaL LGF BEIS profile + CF funding |  |  |  | 14520000 | 45787235 | 37987644.27 | [5 empty] | 35760070.46 | [8 empty] | 23070077.745 | 26160529.82 | 146001345
Total LGF 1/2/3 spend | 359625739.87 |  | 139591213 | 26819999.52 | 26068706.73 | 18243475.81 | 4242173 | 4336074.72 | 2255245.95 | 7409982.14 | 80742059.66 | 20924762.715 | 1445743 | 3439971.34 | 2603380 | 3686438.05 | 2554850 | 325732.9 | 2607217.71 | 8191269.825 | 21814753.925 | 24840999 | 140499310.6
Difference |  |  |  | -12299999.52 | 19718528.27 | 19744168.46 | [5 empty] | 14835307.745 |  | 9733627.1 | [5 empty] | 8191269.825 | 1255323.82 | 1319530.82
Major Transport Schemes | [5 empty] | 92056944.775
Poynton Relief Road | 0 |  | 16400000 | [7 empty] | 0
Crewe High Growth City – Congleton Link Road | 89600000 |  | 45000000 |  | 3500000 | [5 empty] | 3500000 | 12500000 | [8 empty] | 27500000 |  | 47000000
Total Retained majors | 89600000 | 0 | 61400000 | 0 | 3500000 | 0 | 0 | 0 | 0 | 0 | 3500000 | 12500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27500000 | 0 | 47000000
Total LGF | 449225739.87 |  | 200991213 | 26819999.52 | 29568706.73 | 18243475.81 | 4242173 | 4336074.72 | 2255245.95 | 7409982.14 | 84242059.66 | 33424762.715 | 1445743 | 3439971.34 | 2603380 | 3686438.05 | 2554850 | 325732.9 | 2607217.71 | 8191269.825 | 49314753.925 | 24840999 | 187499310.6
Middlewich Bypass | 60250000 |  | 48057000 |  | 1808000 | [5 empty] | 2632000 | 875000 | [8 empty] | 10208000 | 26301000 | 41824000 | updated May 18. £1.257m secured fom DfT. Project not due to complete until 2021. No funding will come through LEP.
A500 dualing | 55000000 |  | 45000000 | 0 | 0 | [5 empty] | 0 | [10 empty] | 1000000 |  | DfT given £2m development grant. May not start until 2021
Total | 115250000 | 0 | 416848213 | 0 | 1808000 | 0 | 0 | 0 | 0 | 0 | 2632000 | 875000 | [8 empty] | 10208000 | 27301000 | 860311461.61
LGF Revenue
Growth Hub |  |  | 287000 |  |  | 287000 | 77500 | 77500 |  |  |  |  | 67500 | 68516.67 | 71000 |  | 76500 |  |  | 72000 |  |  | 574000
Management Charge (1%) |  |  | 428930 |  |  | 107233 | [5 empty] | 107232.5 | [8 empty] | 107233 | 107233 | 428931.5
GPF
Opening Balance |  |  | 12100000 |  |  | 12100000 | [5 empty] | 11425625
Cheshire Green Employment Park |  |  | 3200000 |  |  | 1275000 | 150096.46 | 524278.54 |  |  |  | 1925000 | [10 empty] | 3200000
Glasshouse Alderley Park | 26950000 |  | 3872876
Total | 26950000 |  | 3200000 | 0 | 0 | 1275000 | 150096.46 | 524278.54 | 0 |  |  | 1925000 | [8 empty] | 0 | 0 | 3200000
LEP total spend by year | 501825739.87 |  | 559639426 | 26819999.52 | 27876706.73 | 19518475.81 | 4392269.46 |  |  |  |  | 23724762.715 | [8 empty] | 32022753.925 | 52141999 | 186496967.16 |  |  | No. Projects | Total Costs | Total Grant | Total paid | Still to claim
[25 empty] | LGF 1/2 Projects Completed | 9 | 104460313.74 | 45059600 | 45059600 | 0
|  |  | 147388315 | [21 empty] | LGF 1/2 Projects live | 10 | 258381158.13 | 109894543 | 28528678.29 | 81365864.71
|  |  | 48283298 | [21 empty] | LGF3 live | 15 | 82593070 | 42839070 | 4079529.87 | 38759540.13
[25 empty] | Sub total |  | 362841471.87 | 197793213 | 77667808.16 | 120125404.84
[25 empty] | major transport schemes (poynton and congleton covered under LGF1/2) | 2 | 115250000 | 93057000 | 0 | 93057000
[25 empty] | Total | 2
249
Note on D22: Rachel Brosnahan: £2.35m from LTB)
Note on B36: Rachel Brosnahan: Could be as high as £90m

## Funding split
Project | Total project cost (£) | LGF grant | Private Match £ | Public Match £ | LGF Grant % | Private Match % | Public Match % | Check | Comment
LGF1/2
Completed Projects
Chester Central | 21637682 | 13500000 |  |  | 62.3912 | 0 | 0 | 62.3912
Thornton Science Park | 17382850 | 6800000 |  |  | 39.119 | 0 | 0 | 39.119
Housing Fund Revenue (CWAC) | 7500000 | 7500000 |  |  | 100 | 0 | 0 | 100
DfT Tail majors including Crewe Green Link Road | 25747350 | 4800000 |  |  | 18.6427 | 0 | 0 | 18.6427
Birchwood Pinchpoint | 4986000 | 2140000 |  |  | 42.9202 | 0 | 0 | 42.9202
Live Projects
Sydney Road Bridge | 10378000 | 5850000 | 4028000 | 500000 | 56.3692 | 38.8129 | 4.8179 | 100 | £.5m LTP and £4.028m S106
Crewe Green Roundabout | 7500000 | 3300000 | 2250000 | 1950000 | 44 | 30 | 26 | 100 | £1.95m NPIF, £2.25m S106
GM & Cheshire Life Science Investment Programme | 31982000 | 10000000 | 6076580 | 15671180 | 32.573 | 18.567 | 48.86 | 100
Reaseheath Agri Tech Centre | 7000000 | 2475000 |  |  | 35.3571 | 0 | 0 | 35.3571
Reaseheath Learning Hub and Accommodation | 9980000 | 3556000 |  |  | 35.6313 | 0 | 0 | 35.6313
Reaseheath Employer Focused Hub | 2045000 | 674850 |  |  | 33 | 0 | 0 | 33
Reaseheath Sports Science and Performance Academy (osprey) | 6000000 | 2170000 |  |  | 36.1667 | 0 | 0 | 36.1667
M62 J8 Junction Improvements (Omega) | 11690000 | 5000000 | 1864000 | 4826000 | 42.7716 | 15.9453 | 41.2831 | 100 | £4.826m of S106, £3m HE and £1.826m WBC
Warrington Waterfront (Centre Park Link) | 19891000 | 5300000 | 0 | 14591000 | 26.6452 | 0 | 73.3548 | 100 | £10,095,096 WBC, £3,685,904 HIF
Warrington West Station | 19694000 | 6530000 | 1854000 | 11310000 | 33.1573 | 9.414 | 57.4287 | 100 | £1,854000 S106. £7.08m WBC, £4.23m New stations Fund
Ellesmere Port Central Development Zone | 32000000 | 8332228 |  |  | 26.0382 | 0 | 0 | 26.0382
Ellesmere Port and Chester Campus remodelling | 3791198 | 3198000 |  | 593198 | 84.3533 | 0 | 15.6467 | 100 | £593198 of college funding
Poynton Relief Road | 38000000 | 5600000 |  |  | 14.7368 | 0 | 0 | 14.7368
Crewe High Speed-ready Heart Town Centre Regeneration Programme | 24700000 | 10000000 |  | 14700000 | 40.4858 | 0 | 59.5142 | 100 | £14.7m CEC
Unlocking Winsford Industrial expansion Land | 10900000 | 3800000 | 5900000 | 1200000 | 34.8624 | 54.1284 | 11.0092 | 100
Tarvin Road | 5427000 | 3663000 | 40617 | 1741000 | 67.4959 | 0.74842 | 32.0803 | 100.3246 | £40,167 s106, £1.741m CWAC
Warrington East Highways Improvements | 13500000 | 6900000 |  |  | 51.1111 | 0 | 0 | 51.1111
Omega Local Highways Schemes phase 2 | 6465000 | 4300000 |  |  | 66.512 | 0 | 0 | 66.512
Skills | 5000000 | 5026150 |  |  | 100.523 | 0 | 0 | 100.523
Energy Innovation | 4151070 | 4151070 |  |  | 100 | 0 | 0 | 100
Joint Cheshire and Warrington Sustainable Travel Access Fund | 7750000 | 5000000 |  |  | 64.5161 | 0 | 0 | 64.5161
£25k Skills Call | 26190 | 26190 |  |  | 100 | 0 | 0 | 100
Total value of LGF projects | 355124340 | 139592488 | 22013197 | 67082378 | 39.3081 | 6.1987 | 18.8898 | 64.3966
Major Transport Schemes
Poynton Relief Road | as above | 16400000
Crewe High Growth City – Congleton Link Road | 89600000 | 45000000 |  |  | 50.2232 | 0 | 0 | 50.2232
Total LGF allocation | 444724340 | 200992488 | 22013197 | 67082378 | 45.1948 | 4.9499 | 15.084 | 65.2287
Middlewich Bypass | 60250000 | 48057000 |  |  | 79.7627 | 0 | 0 | 79.7627
A500 dualing | 55000000 | 45000000 |  |  | 81.8182 | 0 | 0 | 81.8182
Total | 115250000 | 93057000 | 0 | 0 | 80.7436 | 0 | 0 | 80.7436
Total value of projects | 559974340 | 294049488 | 22013197 | 67082378 | 52.5112 | 3.9311 | 11.9795 | 68.4219
LGF Revenue
Growth Hub |  | 287000 |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Management Charge (1%) |  | 428930
GPF
Opening Balance |  | 12100000
Cheshire Green Employment Park |  | 3200000 |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Total | 0 | 3200000 | [5 empty] | 0
Note on C10: Rachel Brosnahan: £2.35m from LTB)
Note on B24: Rachel Brosnahan: Could be as high as £90m

## projects broken down by LA
Projects broken down by Local Authority
| Total Project Cost | Intervention Rate | LGF/DFT grant funding | Spent to date | Current status
Cheshire East Council
Sydney Road Bridge | 10497000 | 55.7302 | 5850000 | 1311365 | Jacobs have been appointed to manage the project. Public consultation complete. Planning approved. Rail possessions booked. Conditional offer letter issued by LEP and first claim paid
Crewe Green Roundabout | 7423000 | 44.4564 | 3300000 | 1193328 | Balfour Beatty appointed to take project through to pre-construction. Order plaecd with BT for diversions. Public consultation complete. Planning app submitted. Conditional Offer from LEP issued in March. First claim paid.
Crewe High Speed-ready Heart Town Centre Regeneration Programme | 97000000 | 10.3093 | 10000000 | 0 | Appointed Bus case consultants. Will taking project to P&I for conditional approval in September
Poynton Relief Road | 38000000 | 43.1579 | 16400000 | 3360035 | Planning permission from both Las granted. Drafting CPOs. Expect enquiry early 2018.
Middlewich Bypass | 58483982 | 79.9877 | 46780000 | 2061513 | Outline business case being finalised. Detailed design work commenced.
Crewe High Growth City – Congleton Link Road | 90743268 | 49.5905 | 45000000 | 7222090 | CPO enquiry finished. OJEU works notice due to be published in July. Due to award contact in January 18. On site September 18.
A500 dualing | 57000000 | 78.9474 | 45000000 | 585313 | Project board established. Design work progressing. Most ecological and topographical studies complete.
Total | 359147250 |  | 172330000 | 15733644
Cheshire West and Cheshire Council
Ellesmere Port Central Development Zone | 35000000 | 23.8057 | 8332000 | 50000 | Initial design work complete producing 5 options. Seeking to get MOUs signed by end of July and funding package agreed by end of September.
Chester Central | 21000000 | 64.2857 | 13500000 | 21000000 | Bus Interchange complete
Unlocking Winsford Industrial expansion Land | 5000000 | 76 | 3800000 | 0 | Planning application in for Tiger trailer site but wider planning appliation for the site not ready. Business case consultant appointed through LLP.
Tarvin Road | 5427000 | 67.4959 | 3663000 | 0 | Business case consultants appointed. Due to got to January P&I
total | 66427000 |  | 29295000 | 21050000
Warrington Brough Council
M62 J8 Junction Improvements | 11690000 | 42.7716 | 5000000 | 3020000 | Construction started on site in January 17 and due to complete in April 18. Project has slipped one month.
Warrington Waterfront (Centre Park Link) | 19350000 | 27.3902 | 5300000 | 2757000 | 3 rounds of public consultation completed. Planning approved. LEP conditional offer lette issued and first claim paid
Warrington West Station | 18415000 | 35.4602 | 6530000 | 2245000 | LEP conditional offer lette issued and first claim paid. Planning application submitted.
Warrington East Highways Improvements | 35000000 | 19.7143 | 6900000 | 0 | Consultation events carried out. Business case due to be presented to P&I in November.
OMEGA - Birchwood Pinchpoint | 3620000 | 59.116 | 2140000 | 3620000 | Complete
Omega Local Highways Schemes phase 2 | 6465000 | 66.512 | 4300000 | 0 | Initial design work undertaken.
Total | 94540000 |  | 30170000 | 11642000
Sub-regional Projects
Skills | 5000000 | 100 | 5000000 |  | Skills strategy being written. There will then be a call for projects.
Energy Innovation | 4151070 | 100 | 4151070 |  | Strategy due to be completed in Autumn. There will then be a call for projects
Joint Cheshire and Warrington Sustainable Travel Access Fund | 14250000 | 35.0877 | 5000000 |  | Waiting for agreement between autorities as to which shemes to deliver
Total | 23401070 |  | 14151070
Note on B17: Rachel Brosnahan: Could be as high as £90m

## Ellesmere Port
Ellesmere Port Schemes
Name | Total project costs (£) | LGF (£) | Status
Thornton Energy Demonstrator | 17382850 | 6800000 | Complete. Part occupied
Ellesmere Port and Chester campus remodelling | 3500000 | 3198000 | Completed
Ellesmere Port Central Development Zone | 17429000 | 8332228 | Seeking outline approval at P&I in October
Sutton Way Boulevard, Ellesmere Port | 1024000 | 640000 | In principle approval given. Awaiting business plan
Total | 39335850 | 18970228

## RAG Status
Summary of project status | 5.10.17
Project Name | Comment | Total Cost (£) | Grant (£) | RAG Status
LGF 1/2
Sydney Road Bridge | In design. Due to start on Site in November 18. Slight issue with land required for crane for bridge | 10497000 | 5850000
Crewe Green Roundabout | Planning permission granted 27.09.17. P&I given full approval | 7423000 | 3300000
Chester Central (Northgate and Bus Interchange) | Bus Station completed and operational. Monthly information now being submitted for Northgate which is really useful. Does show there is significant uncertainty about funding of Northgate scheme and issues with puchasing all the property required. CPO process behind schedule. | 21000000 | 13500000
Birchwood Pinch point | Completed | 3620000 | 2140000 |  | 40.4858
GM & Cheshire Life Science Investment Programme | Fund now invested £6.3m into 14 companies. Not likely to achieve outputs and want to negotiate | 31982000 | 10000000
Reaseheath Agri Tech Centre | On site | 7000000 | 2475000
Reaseheath Learning Hub and Accommodation | Demolition work started. Concern about contactors costs, but College will pick up overspend. | 9980000 | 3556000
Reaseheath Employer Focused Hub | On site | 2045000 | 675000
Reaseheath Sports Science and Performance Academy | On site and going well. | 6000000 | 2170000
Thornton Science Park | Project complete, 5 businesses, employing 13 staff now in the building but the Energy Demonstrator Hall is still empty. | 16744000 | 6800000
M62 J8 Junction Improvements | On site, going very well. Due to complete in May 18. | 11690000 | 5000000
Centre Park Link | Compulsory Purchase Order process has started. Peel have now agreed a price for the bridging rights, but still dispute with Maro over land values. Two smaller pieces of land also required. Whole programme has been pushed back 15mths to cover. Could be bought forward if agreement can be reached over the land values for the trhee remaining plots required. | 19350000 | 5300000
Warrington West Station | Project progressing well. Due to start on site in December/early January | 18415000 | 6530000
Ellesmere Port Central Development Zone | Design work ongoing. Current design options £12m over budget. Not all stakeholders have signed MOU and still not clear of space requirements of all stakeholders. Funding strategy delayed until November when design work is due to be completed. | 35000000 | 8332000
Ellesmere Port and Chester Campus remodelling | Phase 1 completed. Design work for phase 2 ongoing | 3500000 | 3198000
LGF 3
Crewe High Speed-ready Heart Town Centre Regeneration Programme | Conditional approval from P&I. Council funding approved. Design work progressing. | 69000000 | 10000000
Unlocking Winsford Industrial expansion Land | Outline business case being developed. Due to seek outline approval from P&I in October | 5000000 | 3800000
Tarvin Road | Outline business case being developed. Due to seek outline approval from P&I in January | 5427000 | 3663000
Warrington East Highways Improvements | Design work continuing on what is a five part scheme. Require £2m of Enterprise Zone funding which will need to be cash flowed and is causing some concern at WBC | 13500000 | 6900000
Omega Local Highways Schemes phase 2 | Design work continuing. Work on the business case has commenced. | 6465000 | 4300000
Skills | Awaiting the skills strategy | 5000000 | 5000000
Energy Innovation | Energy Strategy being worked on. Due to be completed in December | 4151070 | 4151070
Joint Cheshire and Warrington Sustainable Travel Access Fund | Call for projects due to be issues as Local authorities cannot reach agreement on priorities. | 7750000 | 5000000
Major Transport Schemes
Poynton Relief Road | Work continuing on CPO process. Public inquiry expected in early 2018. Costs £19m over original budget. CEC working on a funding strategy. | 38000000 | 16400000
Middlewich Bypass | Route options reduced to two and are being further developed. Outline business case being developed. | 58483982 | 46780000
Congleton Link Road | £12m over budget. Progressing through stage 2 tender process. BCR is only showing at 2.2 at the moment. Could become an issue if the costs escalate further. | 90743268 | 45000000
A500 dualing | Consultation events due to be held. Design work continuing. BCR is currently low. Needs to tie in with HS2 announcement. | 57000000 | 45000000
GPF
Cheshire Green Employment Park | On site and going well. Recently received press coverage. | 14000000 | 32000000
Note on C22: Rachel Brosnahan: Could be as high as £90m

## Qtr spend
Spend by Quarter breakdown
Project | Profiled 17/18 | Actual Q1 17/18 | Actual Q2 17/18 | Total for 17/18
LGF1/2
BEIS funding Profile | 7920938
Growth Hub | 287000 | 77500 | 77500 | 155000
Sydney Road Bridge | 2279000 | 530646 | 117000 | 647646
Crewe Green Roundabout | 1980000 | 962527 | 0 | 962527
Chester Central | 0 | 0 | 0 | 0
Birchwood Pinchpoint | 0 | 0 | 0 | 0
GM & Cheshire Life Science Investment Programme | 2500000 |  | 1710097.72 | 1710097.72
Reaseheath Agri Tech Centre | 323500 |  | 323500 | 323500
Reaseheath Learning Hub and Accommodation | 612084 |  | 612084 | 612084
Reaseheath Employer Focused Hub | 221850 |  | 104172 | 104172
Reaseheath Sports Science and Performance Academy (osprey) | 443775 |  | 443775 | 443775
Thornton Science Park | 0 |  |  | 0
M62 J8 Junction Improvements (Omega) | 2523014 | 1660000 |  | 1660000
Warrington Waterfront (Centre Park Link) | 424000 | 424000 | 0 | 424000
Warrington West Station | 3195000 | 665000 |  | 665000
Ellesmere Port Central Development Zone | 165000 |  |  | 0
Ellesmere Port and Chester Campus remodelling | 826000 |  | 546425 | 546425
Total LGF 1/2 spend | 15780223 | 4319673 | 3934553.72 | 8254226.72
Funding defrayed on CEC projects |  | #REF!
LGF3
BEIS funding Profile | 10348178
Crewe High Speed-ready Heart Town Centre Regeneration Programme | 600000 | 0 | 0
Unlocking Winsford Industrial expansion Land | 712000
Tarvin Road | 200000
Warrington East Highways Improvements | 1650638.86
Omega Local Highways Schemes phase 2 | 250000
Skills | 0
Energy Innovation | 0
Joint Cheshire and Warrington Sustainable Travel Access Fund | 100000
Management Charge (1%) | 107233
Total LGF3 Spend | 3619871.86 | 0 | 0
Difference between profile and forecast spend | 6728306.14
TotaL LGF BEIS profile + CF funding | #REF!
Total LGF 1/2/3 spend | 19400094.86 | 4319673 | 3934553.72
Difference | #REF!

## Transport schemes
Project Name | Total Cost | LGF grant | Notes
DfT Tail majors including Crewe Green Link Road | 25747350 | 4800000 | Complete
Birchwood Pinchpoint | 4986000 | 2140000 | Complete
Sydney Road Bridge | 10378000 | 5850000 | Phase one on site. Main works due to start on site in October
Crewe Green Roundabout | 7500000 | 3300000 | Phase 3 just started. Scheme due to complete in October
M62 J8 Junction Improvements (Omega) | 11690000 | 5000000 | Complete
Warrington Waterfront (Centre Park Link) | 19891000 | 5300000 | Land negoatiations ongoing. Hopefully will in January 19
Warrington West Station | 19694000 | 6530000 | On site. Due to complete September 19
Poynton Relief Road | 38000000 | 5600000 | In development. Awaiting planning inspector review
Tarvin Road | 5427000 | 3663000 | FBC being developed
Warrington East Highways Improvements | 13500000 | 6900000 | On site
Omega Local Highways Schemes phase 2 | 6465000 | 4300000 | In development.
Joint Cheshire and Warrington Sustainable Travel Access Fund | 7750000 | 5000000 | 8 schemes across cheshire and warrington. All in development
Total | 171028350 | 58383000
Major Transport Schemes
Poynton Relief Road | As above | 16400000 | as above
Crewe High Growth City – Congleton Link Road | 89600000 | 45000000 | Contractor just appointed
Middlewich Bypass | 60250000 | 48057000 | In development
A500 dualing | 55000000 | 45000000 | In development
Sub Total | 204850000 | 154457000
Total of all schemes | 375878350 | 212840000
Note on C4: Rachel Brosnahan: £2.35m from LTB)